## Sheet1
2-Dec-2021 To 6-Dec-2021
User Stories | Name | Start On | End On | Status
Project structure, DB setup, Model creation & Remote repo setup | Sahil Yadav | 2021-12-02 | 2021-12-02 | Completed
Database model creation | Savita Choudhary | 2021-12-02 | 2021-12-03 | Completed
As a user I want to signup | Rohit Nakwal | 2021-12-04 | 2021-12-06 | Completed
Raw data in database updation for testing the application | Sahil Yadav | 2021-12-06 | 2021-12-06 | Completed
Creating signup API with validation | Savita Choudhary | 2021-12-06 | 2021-12-08 | Completed
As a user I want to Manage profile section in frontend. | Simran Yadav | 2021-12-06 | 2021-12-08 | Completed
Creating filter api | Tushar Darpe | 2021-12-06 | 2021-12-09 | Completed
7-Dec-2021 To 9-Dec-2021
User Stories | Name | Start On | End On | Status
As a user, I want to validate my details while registering myself. | Rohit Nawal | 2021-12-07 | 2021-12-08 | Completed
Designing Admin panel | Vishal Chouhan | 2021-12-07 | 2021-12-16 | Completed
Navigation handling (Register to Login ) | Saurabh Rai | 2021-12-07 | 2021-12-10 | Completed
Creating login Api and authentication in backend | Savita Choudhary | 2021-12-08 | 2021-12-10 | Completed
As a user I want to see current and previous order (front-back) | Sahil Yadav | 2021-12-07 | 2021-12-08 | Completed
As a user I want to buy package for placing orders (front-back) | Sahil Yadav | 2021-12-09 | 2021-12-09 | Completed
As a user I want to Login to the website. | Rohit Nawal | 2021-12-09 | 2021-12-13 | Completed
10-Dec-2021 To 13-Dec-2021
User Stories | Name | Start On | End On | Status
As a user I want to search books. | Tushar Darpe | 2021-12-10 | 2021-12-16 | Completed
As a user I want to update user details. | Simran Yadav | 2021-12-10 | 2021-12-16 | Completed
As a user I want to know that my email is available or not. | Rohit Nakwal | 2021-12-10 | 2021-12-11 | Completed
As a user I want to validate my details while login | Rohit Nakwal | 2021-12-11 | 2021-12-13 | Completed
As a user I want to add/remove book from the cart (frontend+backend) | Sahil Yadav | 2021-12-11 | 2021-12-13 | Completed
As a user I want to update the shipping address and place the order. | Sahil Yadav | 2021-12-10 | 2021-12-10 | Completed
Created a search box componet | Tushar Darpe | 2021-12-11 | 2021-12-16 | Completed
Created suggested books(best sellers) component | Tushar Darpe | 2021-12-11 | 2021-12-16 | Completed
As a admin I want to add book. | Vishal Chouhan | 2021-12-11 | 2021-12-13 | Completed
As a admin I want to delete a book. | Vishal Chouhan | 2021-12-11 | 2021-12-13 | Completed
As a admin I want to edit book data | Vishal Chouhan | 2021-12-13 | 2021-12-16 | Completed
As a user I want to navigate after login | Sourabh Rai | 2021-12-11 | 2021-12-14 | Completed
14-Dec-2021 To 16-Dec-2021
User Stories | Name | Start On | End On | Status | Integration
As a user I want to update profile details & address (frontend + backend) | Simran Yadav | 2021-12-10 | 2021-12-16 | Completed | Integreated
As a user I want to naivaget throghout the application after login (frontend) | Sourabh Rai | 2021-12-11 | 2021-12-14 | Completed | Integreated
As an admin I want to add book, edit book details & delete book (frontend+backend) | Vishal Chouhan | 2021-12-14 | 2021-12-16 | Completed | Integreated
As a user I want to see suggested and filtered books (frontend + backend) | Tushar Darpe | 2021-12-11 | 2021-12-16 | Completed | Integreated
As a user I want to be authenticated while login and signup with demo-api (backend) | Rohit Nakwal | 2021-12-14 | 2021-12-15 | Completed | Integreated
As a user I want to place return book order (frontend + backend) | Sahil Yadav | 2021-12-14 | 2021-12-14 | Completed | Integreated
Header/Routes/URL Access/Header access logic | Sahil Yadav | 2021-12-15 | 2021-12-15 | Completed | Integration
User profile/Admin panel/Admin header/Suggested books with filter | Sahil Yadav | 2021-12-16 | 2021-12-16 | Completed | Integration
User authentication using passport + middleware creation (backend) | Savita Choudhary | 2021-12-10 | 2021-12-16 | Completed | Integrated
17-Dec-2021 To 21-Dec-2021
User Stories | Name | Start On | End On | Completed | Integration
As a admin I want to see list of orders placed by users (front + back) | Sourabh Rai | 2021-12-17 | 2021-12-21 | Completed | Integrated
Book search filter optimization (Book Name, Author, Category) (front + back) | Tushar Darpe | 2021-12-17 | 2021-12-21 | Completed | Integrated
New user address updation in profile component (front + back) | Simran Yadav | 2021-12-17 | 2021-12-18 | Completed | Integrated
Reset password after login with password authentication (front + back) | Rohit Nakwal | 2021-12-17 | 2021-12-18 | Completed | Integrated
Passport authentication and forget password with validation (front + back) | Savita Choudhary | 2021-12-17 | 2021-12-21 | Completed | Integrated
As a admin I want to see list of return orders placed by users (front + back) | Vishal Chouhan | 2021-12-17 | 2021-12-21 | Completed | Integrated
As a admin I want to upload/edit/view book image along with book data (front + back) | Sahil Yadav | 2021-12-17 | 2021-12-21 | Completed | Integrated